## 1. Social Marketing Activities
Up-Scaling Basic Sanitation for the Urban Poor (UBSUP) | [5 empty] | SafiSan Project |  |  |  | WSP:
Social Marketing Activities | [5 empty] | 1
[7 empty] | Prepared by: |  | CATHERINE NJOKI
Period:
Category | No. | Activity | No. of sessions | No. (1) | Category (2) | Justification | Tool(s)? | Status (3) | Deadline | Person(s) responsible | Remarks:
Preparation | 1 | Training of the Sanitation Marketers (including simulations) |  |  | B | To ensure success of the social marketing | No | N |  | PTT (5)
| 2 | Preparatory meeting of the PTT & Social Animators |  |  | A
| 3 | Establishing contacts within the area |  |  | A
| 4 | The transect walk |  |  | B/D
| 5 | Collecting of additional information on the area |  |  | D
| 6 | Preparing outputs of the transect walk and data collection |  |  | A/H
| 7 | Preparing the Social Marketing Programme |  |  | A
| 8 | (Construction of) SafiSan demonstration toilets |  |  | A/F
| 9 | Meeting with Artisans |  |  | B
| 10 | Meeting with Manual Emptiers |  |  | B
| 11 | Visiting the SafiSan demonstration toilet |  |  | B
| 12 | School WASH programme |  |  | E1
| 13 | Message broadcast on local radio station |  |  | E1/E2
| 14 | Message broadcast on local television station |  |  | E1/E2
Social marketing | 15 | PA announcement |  |  | E1/E2
| 16 | SafiSan Baraza (4) |  |  | E1/E2
| 17 | SafiSan Mini Fairs |  |  | E1/E3
| 18 | Drama (or music) group performances |  |  | E1/E2
| 19 | Putting up posters |  |  | E1/E2/E3
| 20 | Distributing brochures |  |  | E3
| 21 | Distributing flyers |  |  | E3
| 22 | Residents visiting the SafiSan demonstration toilet |  |  | E1/E3
| 23 | Household & plot-level visits |  |  | E3
| 24 | Other:
| 25 | Other:
| 26 | Monitoring (evaluation) of the Social Marketing Programme |  |  | H
| 1): | No. of copies, persons, etc.
| 2): | A = Design & planning; B = Information & training; C = Demand assessment; D = Data collection; E1 = Awareness creation; E2 = Community mobilisation; E3 = Social marketing; F = Technical; G = Disbursement request; H = Reporting
| 3): | N = Not yet started; D = Draft ready; O = On-going; C = Complete; E = Delayed
| 4) | Each community awareness & mobilisation activity such as the SafiSan Mini Fairs and the SafiSan Baraza Shows has its own programme
| 5): | PTT = Project Task Team
| 5): | WSP Team:
| 5): | County Resident Monitors

## 2. Social Marketing Programme
Up-Scaling Basic Sanitation for the Urban Poor (UBSUP) | [5 empty] | SafiSan Project |  |  |  | WSP:
Social Marketing Activities | [5 empty] | 2
[7 empty] | Prepared by: |  | CATHERINE NJOKI |  | Period>> | October - November 2013
[11 empty] | Month>> | October | [30 empty] | November
Category | No. | Activity | No. of sessions | No. (1) | Category (2) | Justification | Tool(s)? | Status (3) | Deadline | Person(s) responsible | Team Day >> | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Preparation | 1 | Training of the Social Animators (including simulations) |  |  | B | Ensure success of social marketing | No | N | 2013-08-23 | PTT (5)
| 2 | Preparatory meeting of the PTT & Sanitation Marketers |  |  | A
| 3 | Establishing contacts within the area (1st visit) |  |  | A
| 4 | The transect walk |  |  | B/D
| 5 | Collecting of additional information on the area |  |  | D
| 6 | Preparing outputs of the transect walk and data collection |  |  | A/H
| 7 | Preparing the Social Marketing Programme |  |  | A
| 8 | Meeting with the Artisans |  |  | A/F
| 9 | Meeting with the Manual Emptiers (Sanitation Teams) |  |  | B
| 10 | Visiting the SafiSan demonstration toilet |  |  | B
Social marketing | 11 | Kick-off meeting for the social marketing programme |  |  | B
| 12 | PA announcements |  |  | E1
| 13 | 1st Baraza Show |  |  | E1/E2
| 14 | etc.
| 15 | etc.
16
17
18
| 1): | No. of copies, persons, etc.
| 2): | A = Design & planning; B = Information & training; C = Demand assessment; D = Data collection; E1 = Awareness creation; E2 = Community mobilisation; E3 = Social marketing; F = Technical; G = Disbursement request; H = Reporting
| 3): | N = Not yet started; D = Draft ready; O = On-going; C = Complete; E = Delayed
| 4) | Each community awareness & mobilisation activity such as the SafiSan Mini Fairs and the SafiSan Baraza Shows has its own programme
| 5): | PTT = Project Task Team
| 5): | WSP Team:
| 5): | WSTF County Resident Monitors

## 3. Social Animator Programme
Up-Scaling Basic Sanitation for the Urban Poor (UBSUP) | [5 empty] | SafiSan Project |  |  |  | WSP:
Social Marketing Activities | [5 empty] | 3
[7 empty] | Social Animator: |  |  |  | Period>> | October - November 2013
[11 empty] | Month>> | October | [30 empty] | November
Category | No. | Activity | No. of sessions | No. (1) | Category (2) | Justification | Tool(s)? | Status (3) | Deadline | Person(s) responsible | Team Day >> | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Preparation | 1 | Training of the Social Animators (including simulations) |  |  | B | Ensure success of social marketing | No | N | 2013-08-23 | PTT (5)
| 2 | Preparatory meeting of the PTT & Social Animators |  |  | A
| 3 | Establishing contacts within the area (1st visit) |  |  | A
| 4 | The transect walk |  |  | B/D
| 5 | Collecting of additional information on the area |  |  | D
| 6 | Preparing outputs of the transect walk and data collection |  |  | A/H
| 7 | Preparing the Social Marketing Programme |  |  | A
| 8 | Meeting with the Artisans |  |  | A/F
| 9 | Meeting with the Manual Emptiers |  |  | B
| 10 | Visiting the SafiSan demonstration toilet |  |  | B
Social marketing | 11 | Kick-off meeting for the social marketing programme |  |  | B
| 12 | PA announcements |  |  | E1
| 13 | 1st Baraza Show |  |  | E1/E2
| 14 | etc.
| 15 | etc.
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
| 1): | No. of copies, persons, etc.
| 2): | A = Design & planning; B = Information & training; C = Demand assessment; D = Data collection; E1 = Awareness creation; E2 = Community mobilisation; E3 = Social marketing; F = Technical; G = Disbursement request; H = Reporting
| 3): | N = Not yet started; D = Draft ready; O = On-going; C = Complete; E = Delayed
| 4) | Each community awareness & mobilisation activity such as the SafiSan Mini Fairs and the SafiSan Baraza Shows has its own programme
| 5): | PTT = Project Task Team
| 5): | WSP Team:
| 5): | WSTF Field Monitors (FMs):

## 4. Social Animator Program (2)
Up-Scaling Basic Sanitation for the Urban Poor (UBSUP) | [5 empty] | SafiSan Project |  |  |  | WSP:
Social Marketing Activities | [5 empty] | 4
[7 empty] | Social Animator: |  |  |  | Period>> | October - November 2013
[11 empty] | Month>> | October | [30 empty] | November
Category | No. | Activity | No. of sessions | No. (1) | Category (2) | Justification | Tool(s)? | Status (3) | Deadline | Person(s) responsible | Team Day >> | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Preparation | 1 | Training of the Social Animators (including simulations) |  |  | B | Ensure success of social marketing | No | N | 2013-08-23 | PTT (5)
| 2 | Preparatory meeting of the PTT & Social Animators |  |  | A
| 3 | Establishing contacts within the area (1st visit) |  |  | A
| 4 | The transect walk |  |  | B/D
| 5 | Collecting of additional information on the area |  |  | D
| 6 | Preparing outputs of the transect walk and data collection |  |  | A/H
| 7 | Preparing the Social Marketing Programme |  |  | A
| 8 | Meeting with the Artisans |  |  | A/F
| 9 | Meeting with the Manual Emptiers |  |  | B
| 10 | Visiting the SafiSan demonstration toilet |  |  | B
Social marketing | 11 | Kick-off meeting for the social marketing programme |  |  | B
| 12 | PA announcements |  |  | E1
| 13 | 1st Baraza Show |  |  | E1/E2
| 14 | etc.
| 15 | etc.
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
| 1): | No. of copies, persons, etc.
| 2): | A = Design & planning; B = Information & training; C = Demand assessment; D = Data collection; E1 = Awareness creation; E2 = Community mobilisation; E3 = Social marketing; F = Technical; G = Disbursement request; H = Reporting
| 3): | N = Not yet started; D = Draft ready; O = On-going; C = Complete; E = Delayed
| 4) | Each community awareness & mobilisation activity such as the SafiSan Mini Fairs and the SafiSan Baraza Shows has its own programme
| 5): | PTT = Project Task Team
| 5): | WSP Team:
| 5): | WSTF Field Monitors (FMs):